D6.1  Evaluation Plan

Project information

| Grant Agreement Number | 2017 - 2863 / 001 - 001 |
| --- | --- |
| Project Full Title | Towards responsive engineering curricula through europeanisation of dual higher education |
| Project Acronym | DYNAMIC |
| Funding scheme | 588378-EPP-1-2017-1-DE-EPPKA2-KA |
| Start date of the project | 01-11-2017 |
| Duration | 36 months |

Deliverable Information

| Deliverable n° | 6.1 |
| --- | --- |
| Deliverable title | Evaluation plan |
| WP | WP6 |
| WP Leader | Mrs Evgenia Mahler |
| Contributing Partners | HSW |
| Authors | Evgenia Mahler (HSW) |
| Contributors | Rodica Ciudin (HSW) |
| Reviewers | Regina Krause (HSW) |
| Contractual Deadline | 12/2017 |

Dissemination Level

| PU | Public |  |
| --- | --- | --- |
| PP | Restricted to other programme participants (incl. Commission Services) |  |
| RE | Restricted to a group specified by the consortium (incl. Commission Services) |  |
| CO | Confidential, only for the members of the consortium (incl. Commission Services) | X |

Document Log

| Version | Date | Description of Change |
| --- | --- | --- |
| V1.0 | 31/01/2018 | Document Draft |
| V.1.1 | 10/02/2018 | First revision |
| V.1.2 | 05/03/2018 | Second revision |
| V.2.0 | 09/03/2018 | Final draft |
| V.3.0 | 10/03/2018 | Final report |

Content

Project structure and expected outcomes	4

Introduction	5

Objectives of the evaluation	6

Evaluation subject	6

Indicators	7

Evaluation methodology	11

Data collection	11

Evaluation methods and instruments	12

Evaluation timeline	16

Responsibilities of the evaluation team	18

Bibliography	19

Annexes	20

# Project structure and expected outcomes

The project addresses the need for more flexible routes for acquiring current industry-related skills necessary in the Manufacturing sector. For this purpose, regular practical phases in enterprises will be integrated in the ongoing engineering curricula to accelerate the update of knowledge traditionally provided by higher education institutions. To achieve that the project will apply the model of dual higher education, which is well-established in Germany and Austria. The aim of the project is to develop, implement, test and validate the content for the practical phases, and establishing the foundation for introducing 3 dual practice-integrated higher education programmes in the partner universities in Bulgaria, Romania and Croatia.

Project methodology:

Focus groups of academic and industrial representatives will review the curricula of 3 undergraduate programmes from the domain of Mechanical Engineering, Mechatronics and Shipbuilding selected for the regional needs in the partner countries. The focus groups will define the training needs for urgently required skills, define practical exercises related to the taught programme modules, mapped the developed practical phases with ECTS. The curricula adaptation process is subject to WP2. The practical phases developed for the future dual programmes will be piloted in WP5.

In order to ensure successful implementation, the project will develop in WP3 a toolkit for documentation and assessment of the practical training for academic supervisors. To strengthen the training capacities of the enterprises involved in dual education, the project will develop in WP4 materials for a certificate training course of industrial supervisors.

In WP6, the knowledge and experience gained within the project will be synthesised in a methodological document that will describe the different sets of methods employed at the different stages of the process in curricula adaptation, validation and implementation.

Active involvement of the stakeholders and planned dissemination measures will ensure sustainable long-term exploitation of project results beyond the project life-time and outside the partnership.

To reach this goal the project follows the logic as described below:

- Description of developing steps for a dual study programme

- Curriculum adaptation and approval process

- Preparation of implementation and training of staff

- Pilot implementation

- Evaluation and documentation

The above described steps are related to the following project outcomes:

- Process flowchart with guidelines and working procedures (WP3)

- National descriptive reports and approved dual curricula (WP2)

- Toolkit for implementation and documentation of practical phases (WP3), “Train the Trainer” course for industrial supervisors in dual higher education programmes (WP4)

- Implementation reports (WP5)

- Methodological guidelines for design and implementation of dual practice-integrated programmes (WP6)

# Introduction

The “Dynamic” project addresses in WP6 the transferability of project results for adaption in other settings such as to:

- other fields of study to further higher education institutions

- further enterprises in the partner countries,

- extend results application to other countries.

Since the dual education form is a new approach for higher education institutions in Bulgaria, Romania and Croatia, there is a need for methodological description of the entire process from the curriculum adaptation, elaboration of the practical phases, formal approval and implementation of a dual programme in the country-specific context. The purpose of the project evaluation is to capture all steps and methods involved, while ensuring a certain degree of comparability between the countries.

The objective of this document is to describe the:

- key project elements (deliverables, events, processes) that will be subject to evaluation

- indicators against which the these elements will be evaluated

- evaluation activities and methods to be applied

- timeframe and responsibilities

# Objectives of the evaluation

The aim of the evaluation plan is to ensure that all partners understand the data and information that are required for evaluation of the project, and to ensure that once collected, the data offer a useful insight to the project work and contribute for the production of a good-quality results.

The objectives that apply for this evaluation plan are:

- Analyse the process of implementation, focusing on stakeholder participation

- Analyse empirical findings acquired throughout the project

- Identify key areas of knowledge and success factors in order to formulate guidelines for knowledge transfer outside the project

- Identify problems and constraints that have been encountered

- Identify important lessons to be learnt and make recommendations for the implementation of future actions

# Evaluation subject

The project elements that will be subject to evaluation are derived from the main expected results of the project. The key project deliverables, events and processes that will be a subject to evaluation in WP6 are listed in the table below:

| Type | WP | ID | The key project deliverables, events and processes subject to evaluation and quality review. | Reporting form | Delivery | WP6 activity |
| --- | --- | --- | --- | --- | --- | --- |
| Process | 2 | T2.2 | Regional focus group meetings (curricula development process) | Consolidated report | M8 | Report template |
| Deliverable | 2 | D2.4 | Approved dual curricula for dual implementation | National reports | M12 | Report template Comparative analysis of provided reports |
| Deliverable | 3 | D3.2 | Toolkit of templates and checklist for documentation and assessment | Templates, handouts and checklists | M8 | End-user survey |
| Deliverable | 4 | T.4.3 | Course and training materials | Training report | M19 | Training evaluation form |
| Process | 5 | T.5.1 T.5.2 T.5.3 | Pilot implementations of the dual programmes in Sibiu, Varna and Pula | Implementation reports | M25 | Comparative report structure Self-evaluation and improvement plans |
| Process | 5 | T.5.4 | Study visits in Sibiu, Varna and Pula | Peer review report | M29 | Define evaluation criteria Peer review report template |
| Deliverable | 6 | D.6.5 | Methodological Guidelines | Publication | M35 | Feedback form |
| Events | 7 | D7.4-5 | Dissemination and targeted events | Event reports |  | Event evaluation form |

The evaluation foreseen by the project can be categorised as follows:

Process/implementation evaluation, which will determine whether the project activities have been implemented as intended and if the project activities resulted in the planned outcomes described in the application form.

Outcome evaluation, which will be assessing the progress in the outcomes or outcome objectives that the projects is to achieve, as well as the effect of the outcomes on the target groups.

Impact evaluation measures are foreseen at the end of the project to assess how effective the project was in achieving its ultimate goal.

The process and outcome evaluation will be performed by internal evaluator. The results of the internal evaluation will be presented in 2 internal evaluation repots (D.6.3 and D.6.4). The impact evaluation will be performed by an external evaluator, who will produce one external evaluation report and an improvement plan for the further implementation of the new dual programmes.

# Indicators

In order to analyse the level of achievement of project objectives and the relevance of the outputs and outcomes with respect to what was declared in the project description form, a number of indicators has been defined. The table of indicators identifies activities, outcomes and expected outputs for each work package.

| WP | WP leader | Indicators |
| --- | --- | --- |
| WP1 | HSW | 1 consortium agreement signed between the coordinator and each partner 7 project meetings organised 6 project board meetings organised 80% level satisfaction from project meetings 1 interim and 1 final reports produced on time 1 web-based communication tool established 1 monitoring and implementation report in M13 |
| WP2 | LBUS | 1 meeting report from Transnational stakeholder workshop in M2 3 practice-integrated dual programmes developed and approved 9 focus group meetings (FGM) organised (LBUS, TUV and PTP each 3) 9 agendas and meeting notes from FGM 3 consolidated FGM reports (LBUS, TUV and PTP each 1) 3 contractual templates in national languages 3 reports on approved dual curricula (LBUS, TUV and PTP each 1) |
| WP3 | FHJ | 15 academic supervisors trained 80% level satisfaction from training workshop 80% satisfaction with the developed tools 1 process flowchart for development of dual higher education programmes Number of tools and templates developed |
| WP4 | AHK BG | 12 industrial supervisors trained 80% level satisfaction from seminars/ events 3 training courses with customised & translated training materials At least 9 chamber instructors trained (3 per chamber) 3 national face-to-face training workshops in M31 (1 in each BG, RO, HR) Nr. of trainings to industrial stakeholders outside the partnership within the project lifetime (15-20 in each BG/RO/HR) |
| WP5 | TUV | 25 student placements created by the project At least 80% level of satisfaction from student placements Nr. of students registered for the selection process 3 implementation reports (LBUS, TUV and PTP each 1) |
| WP6 | HSW | Number of evaluation tools and templates developed 2 interim evaluation reports produced on time 1 final evaluation report produced by external evaluator 1 Guidelines produced and translated by the end of the project |
| WP7 | RAABE/HSW | 550 participants on targeted events 3000 visits on the project website 80% level satisfaction from project events 2000 final project brochures distributed (150 at final conference, the rest by the partners) 6 scientific papers presented on expert conferences 17 articles published in media (6 in national & 11in local media) 2000 stakeholders reached via social media & e-newsletter (target 2000) 250 stakeholders reached via the two dissemination conferences |

Evaluation of short-term results and long-term outcomes during the project lifetime as described in the application form:

| Short term results | Target groups/potential beneficiaries | Quantitative indicators | Qualitative indicators |
| --- | --- | --- | --- |
| Approved updated curricula with applying the dual training approach | Students/universities and industrial companies | Curricula for 3 study programmes | Common undergraduate competences currently required by the labour market integrated into academic curricula |
| Toolkit for implementation & documentation of dual practical phases | Academic teachers | Nr. of teachers applying the new tools Nr. of tool downloads Nr of academic staff trained | Level of satisfaction and feedback from academic and industrial partners |
| Training materials for industrial mentors involved in dual education | Chambers, enterprises, industrial mentors | Industrial stakeholders reached Number of persons trained Number of students required by industrial partners Nr of projects mentored | Level of satisfaction from trainings |
| Student placements for practical-phase training | Students | Nr. of days spent in the enterprises Nr. of projects completed | Improvement of student academic results |
| Knowledge transfer & exchange | Chambers, enterprises, universities, industrial & academic mentors | Nr.of transnational meetings organised Nr of stakeholders involved in knowledge exchange | % of stakeholder satisfaction and feedback |
| Web-based communication platform | Universities, industrial companies, chambers | 1 web-based platform Number of interactions between academic and industrial stakeholders | Real-time communication between partners, transparency and secured data storage |
| Public website | All stakeholders | Nr. of unique visits Nr. of resources uploaded Nr. of pages visited Nr. of output downloads | Average time of visits |

| Long term outcome | Target groups/potential beneficiaries | Quantitative indicators | Qualitative indicators |
| --- | --- | --- | --- |
| New approach of curricula delivery in BG/RO/HR | Students | Nr. of students applying for the dual programmes offered in LBUS, TUV, PTP Nr. of students mentored by industrial stakeholders | Percentage of students integrated within workforce after graduation (in their field of study) |
| New approach of engineering curricula delivery in BG/HR/RO | Shipbuilding & Ship Repair sector Manufacturing & Production sector | Nr. of dual programmes created with Association member enterprises Nr. of applicants for technical jobs with high practical skills | Level of alignment between applicant qualification profile and job profile Level of industry-related competences of the hired specialists |
| Methodological Guidelines | Industrial companies Universities | Nr. of dual programmes in LBUS, TUV, PTP Nr. of HEIs adopting the developed methodologies Nr. of dual higher education programmes in the target countries started outside the partnership | Quality of engineering education offered in the regions of pilot implementation Rating scores of the new dual programmes |
| Training materials for industrial mentors involved in dual education | Chambers, enterprises | Nr. of enterprises reached & trained outside the partnership | Level of course recommendation by trained enterprises |
| Improved innovation environment | Industrial companies | Nr of projects integrated Nr. of patents related to student project and UBC | % of successful transfer in hosting enterprise |
| Network for UBC | Industrial companies Universities | Nr of new dual programmes in the partner HEIs Nr. of long-term cooperation projects between HEIs & enterprises | % of DYNAMIC and new partners |

# Evaluation methodology

Data collection

Type of data: Primary data will be collected to identify the steps and methods involved in the design of practical phases integrated into the adapted curricula steps: identify knowledge gaps and define training needs together with the industrial stakeholders, description of requirements (trainees and companies), content formulation and duration of the practice phases. Primary data collection will be also used during the evaluation of the curriculum implementation process.

Secondary research will be applied to inventory the existing VET and WIL initiatives in BG, RO and HR.

- Data collection methods: Mainly qualitative methods will be used to acquire primary data - such as focus groups (T.2.1), stakeholder interviews, partner meetings, observations, site visits (T.5.4 and T.6.4), field notes.

- Data collection sources: The data will be collected from the project stakeholders in the partner countries. Key role in the data collection process play the partner universities in Bulgaria, Romania and Croatia, which will be coordinating the curriculum development and implementation process.

- Main source of data are partner reports related to the project milestones and work package outcomes. For the purpose of comparability working guidelines and report templates will be developed and provided to the local coordinating partners.

Table F.3: Evaluation Areas and Associated Data Collection Methods

| Evaluation Subject | Data Collection Method | Source of Data | Deliverable | Outcome |
| --- | --- | --- | --- | --- |
| Curriculum development process | Focus group meetings | Focus groups reports | Consolidated focus group reports | 1st evaluation report |
|  | Report template & guidelines | National reports on developed curricula | Comparative report |  |
|  | Partner survey Desk research | Stakeholder questionnaires | Descriptive paper |  |
| Curriculum implementation process | Report template & guidelines | National reports on implementation | Curriculum implementation plan | 2nd evaluation report |
|  | Report template & guidelines | National reports on implementation | National report on implemented programmes |  |
|  | Field survey, observation | Site visits implemented programmes | Peer review reports |  |
|  | Partner survey |  | Self-evaluation reports |  |
|  | Field survey, observation | Site visits and national implementation reports | Comparative analysis | External evaluation report |
|  |  |  | Improvement plan |  |

Evaluation methods and instruments

Focus groups

- Focus group questionnaires

- Focus group reporting template for comparative analysis

Comparative analyses

- Comparative analysis of national reports on curricula development and implementation processes

Desk research

Desk research includes analysis of project and programme documents as well as information given by the partners.

Until the end of July 2018 project partners will elaborate three consolidated focus group reports with module description of the practical phases on developed dual curricula for each country.

The reports will be subject to comparative analysis, considering the national  country specific requirements.

-Stakeholder interviews

- Inventory of country-specific factors and collection of best practices

- Reflection of implemented dual study programmes

Evaluation of Project Meetings, training seminars and targeted events

Data will be collected from all transnational meetings for getting information how the implementation process is going on. Participants’ feedback on the topics, methods, results, the working atmosphere and additional suggestions will be collected after the meetings:

- Feedback questionnaires on targeted events

- Feedback and assessment questionnaires from the in-company trainings

- Survey on management and communication structures

### Schedule of Regional Working Groups Meetings

### Task description: LBUS, TUV and PTP will each organise 3 to 6 regional focus group workshops with the partner enterprises. The working groups will review the curricula of the 3 selected programmes, will analyse the required skills and define practical exercises related to the taught programme modules, and map the developed practical phases with ECTS. Project-based learning approach that relies on guided self-learning of the students will be applied in designing the practical training content. This approach will allow students to continue their work after the in-company training using the university facilities under the guidance of the academic tutor. Better linkage of the two learning locations will be achieved. Where possible, the flexible practical hours will use virtual tools, e.g. “remote engineering” that allows TUV students to connect to KFB’s server to perform practical tasks.

| Focus Group Workshops - Romania |
| --- |
| organizer | partner enterprises | Meeting 1 | Meeting 2 | Meeting 3 |
|  |  | date | location | date | location | date | location |
| Lucian Blaga University of Sibiu | Marquardt Schaltsysteme SCS Sibiu | 26.02.2018 | Lucian Blaga University of Sibiu, Engineering Faculty, 4 E. Cioran st., room IM301 | 26.03.2018 | Lucian Blaga University of Sibiu, Engineering Faculty, 4 E. Cioran st., room IM301 | 07.05.2018 | Lucian Blaga University of Sibiu, Engineering Faculty, 4 E. Cioran st., room IM301 |
|  | Continental Automotive Systems Sibiu |  |  |  |  |  |  |
|  | German- Romanian Chamber of Commerce and Industry |  |  |  |  |  |  |
| Focus Group Workshops - Bulgaria |
| organizer | partner enterprises | Meeting 1 | Meeting 2 | Meeting 3 |
|  |  | date | location | date | location | date | location |
| Technical University Varna | MTG-Dolphin PLC | 21.03.2018 | TU-Varna | 18.04.2018 | TU-Varna | 16.05.2018 | TU-Varna |
|  | Keppel FELS Baltech Ltd |  |  |  |  |  |  |
|  | German-Bulgarian Chamber of Commerce and Industry |  |  |  |  |  |  |
| Focus Group Workshops - Croatia |
| organizer | partner enterprises | Meeting 1 | Meeting 2 | Meeting 3 |
|  |  | date | location | date | location | date | location |
| Polytechnic Pula | Holcim (Hrvatska) d.o.o. | 26.02.2018. | Polytechnic Pula | 29.03.2018. | Polytechnic Pula | 26.04.2018. | Polytechnic Pula |
|  | ULJANIK Shipyard |  |  |  |  |  |  |
|  | Croatian Chamber of Economy |  |  |  |  |  |  |
|  | Region of Istria |  |  |  |  |  |  |

- Peer Reviews

Peers from HSW and FHJ will conduct internal evaluation of the initial implementation of the practical phases following criteria pre-defined in WP6. The peer team will include representatives of student organisations and will use interviews and questionnaires. Recommendations improvement will be formulated in the report that will be jointly prepared by FHJ and HSW. The report will be presented by FHJ at the project meeting in M29 in Wismar.

Based on the recommendation from the peer review report the methodologies will be improved for the implementation of the last practical phase.

The degree of improvement will be reflected after the external evaluation report on project outputs in M35.

Internal project evaluation:

D6.3.1: 1st Internal Evaluation Report (M13)

- Description on how the feasibility study for the programmes was conducted in the preparatory project and how the programmes have been selected, including an updated inventory of existing VET and WIL initiatives in BG, RO and HR (descriptive paper)

- Description on the steps and methods involved in the design of practical phases integrated into the adapted curricula steps: identify knowledge gaps and define training needs together with the industrial stakeholders, description of requirements (trainees and companies), content formulation and duration of the practice phases

(common comparative report from the focus group results in WP2)

D6.3.2: 2nd Internal Evaluation Report (M29)

- Description on the implementation plan including timetable for preparation and implementation of the practical in-company trainings

- Highlights on the adaptive elements of the curricula and the processes chain of adapt/realign, test, validate, and recommendations for the re-accreditation of the programmes (partner reports on approved curricula)

- Highlights the common parts of the 3 updated curricula

- Peer review report after the first practical phase

- Reflection on quantitative and qualitative results from the piloting

External project evaluation:

D6.4 External evaluation report from CWIHE experts in M34

- Comparative study with country-specific recommendations based on the implementation reports of the pilots (comparative analysis)

- Improvement plan for the programmes beyond the project

- Study visits with peer review reports

# Evaluation timeline

The following table presents a timeline for the evaluation activities planned as well as the person in charge for each activity.

Table F.6. Data Collection Plan

| Evaluation Element | Data Collection Method | Activities Needed | Person(s) Responsible | Due Date |
| --- | --- | --- | --- | --- |
| Approved dual curricula for dual implementation | Focus groups | Notes from FGMs | G. Ilieva T. Zufic G. Racz | After each FG meeting |
|  |  | Consolidated FGM reports | G. Ilieva T. Zufic G. Racz | June 2018 |
|  | Activity reporting | Dual curricula and module description | G. Ilieva T. Zufic G. Racz | September 2018 |
|  |  | National reports on approved dual curricula | G. Ilieva T. Zufic G. Racz | November 2018 |
| Toolkit of templates and checklist for documentation and assessment | Feedback questionnaires Self-reflection questionnaires | Prepare training materials for workshop in M8 | H. Hochrinner | May 2018 |
|  |  | Prepare a feedback form | H. Hochrinner | June 2018 |
|  | Training evaluation report | Evaluation of feedback and training report | H. Hochrinner | July 2018 |
| Project management and communication | Partners’ survey | Prepare survey template | E. Mahler | November 2018 |
|  |  | Collect feedback | R. Ciudin | December 2018 |
|  |  | Evaluate survey results | R. Ciudin | January 2019 |
| Course and training materials | User survey/feedback questionnaires | Prepare training course materials | M. Soare M. Erhard | May 2019 |
|  |  | Prepare feedback questionnaires | M. Soare M. Erhard | May 2019 (transnational) After each national |
|  | Training reports | Prepare transnational training report | M. Soare M. Erhard | July 2019 |
|  |  | Prepare national training reports | M. Soare M. Erhard CCE Croatia | March 2020 |
|  |  | Prepare consolidated report on design and implementation | M. Erhard | August 2020 |
|  | Assessment of fulfilment of certificate requirements |  | AHK RO AHK BG CCE Croatia trainers | March 2020 August 2020 |
| Pilot implementations | Activity reporting | Prepare implementation reports | G. Ilieva T. Zufic G. Racz | December 2019 |
|  | Self-reflection | Prepare self-evaluation form | E. Mahler | February 2020 |
|  |  | Fill in self-evaluation form | G. Ilieva T. Zufic G. Racz | February 2020 |
|  | Peer reviews | Monitoring study visits | R. Ciudin | March 2020 |
|  |  | Prepare peer review report | E. Mahler H. Hochrinner R. Larek | April 2020 |
|  | External evaluation | Organise an external evaluation visit | H. Hochrinner | September 2020 |
|  |  | Prepare an external evaluation report | CWIHE expert | October 2020 |
|  |  | Summarise improvement plans | CWIHE expert | October 2020 |
| Methodological Guidelines | Stakeholder involvement | Form working group to write the guidelines | E. Mahler | March 2018 |
|  |  | Prepare and send the assigned part of the guidelines | Each involved partner | June 2018-June 2020 |
|  | Stakeholder feedback | Feedback on draft structure | All partners | March 2018 |
|  |  | Feedback on end draft | All partners | September 2020 |
| Targeted events | User survey | Feedback questionnaires |  | s. attachment (D.7.1) |

# Responsibilities of the evaluation team

- For the management and implementation of this evaluation, a team consisting of project members and external evaluators will be formed. Their role and responsibilities are defined in the table below. An external evaluator from the CWIHE network will be identified when the curriculum implementation process starts.

Table F.5. Roles and Responsibilities of the Evaluation Team Members

| Individual | Role | Responsibilities |
| --- | --- | --- |
| HSW | WP6 leader | Create and propose evaluation plan; coordinate the development of data collection templates and guidelines, develop and monitor evaluation management plan and timeline; perform analyses and data interpretation; dissemination of evaluation results; participates in peer review visits |
| HSW | Project coordinator | Coordinate the development of data collection templates and guidelines, monitor evaluation management plan and timeline; |
| HSW | Responsible for dual programme “Mechanical Engineering” at HSW | Feedback on data collection templates and guidelines; participates in data analysis, interpretation and results dissemination; participates in peer review visits |
| FHJ | Dual programme “Production Technologies and Organisation” at FHF | Feedback on data collection templates and guidelines; participates in data analysis, interpretation and results dissemination; participates in peer review visits |
| TUV | Local coordinator Bulgaria | Organize and document FGM; produce joint FGM report, produce national reports on curriculum development and implementation; Organize peer review in TUV; Produce self-evaluation report; Country-related contribution to D.6.5 (BG-context) |
| LBUS | Local coordinator Romania | Organize and document FGM; produce joint FGM report, produce national reports on curriculum development and implementation; Organize peer review in LBUS; Produce self-evaluation report; Country-related contribution to D.6.5 (RO-context) |
| PTP | Local coordinator Croatia | Organize and document FGM; produce joint FGM report, produce national reports on curriculum development and implementation; Organize peer review in PTP; Produce self-evaluation report; Country-related contribution to D.6.5 (HR-context) |
| RAABE | Member working group “Guidelines” | Review the annual evaluation reports Define the structure of the Guidelines together with HSW Distribute (publish) the guidelines |
| Project board | Each partner institution | Approves changes and corrections |
| Peer review group members | HSW, FHJ | Assure dual curricula is structured and delivered per good academic and training standards Recommend corrective actions and improvement measures |
| External evaluators | CWIHE | Verifies correctness of internal evaluation findings Recommend corrective actions and improvement measures |

# Bibliography

CDC | Types of evaluations in the Program Operations Guidelines for STD Prevention manual on program evaluation

DoIT Project Management Framework| Quality Management Plan, State Asthma Program Evaluation Guide.

GLOBAL SRS | Project Quality Plan and Evaluation Plan